## Sheet1
No | Plan Description | Response Person |  |  | Visit Method | Plan Date/Time | Actual Date/Time | Man Hours | Status | Remark
|  | Implementor | Heng: Dev | Heng: Ops
1 | Preparation Phase
| 1.1 Final Invoice and Payment Document | x | x | x | Remote/Call/Email | 2018-02-19 | 2018-02-18 | 2 | Done
1.2 Start formal inform and request resource
| - Hardware resource for provision docker host | x |  | x | Remote/Call/Email | 19 - 23/2/2018 |  | 1 | Planning
| - VPN access/Remote support solution | x |  | x | Remote/Call/Email | 19 - 23/2/2018 |  | 1 | Planning
| - FTP Server (Backup Server), NTP Server, SysLog etc | x |  | x | Remote/Call/Email | 19 - 23/2/2018 |  | 1 | Planning
| - Collect requirement and design mantis workflow | x | x |  | Remote/Call/Email | 19 - 23/2/2018 |  | 1 | Planning
| 1.3 Confirm Date/Time for site visit (First Times) | x | x | x | Remote/Call/Email | 19 - 23/2/2018 |  | 0.5 | Planning
2 | Onsite Visit & Initial Setup Machine
| 2.1 Join with Heng Dev&Ops team for clarify task |  |  |  | OnSite Visit | 24 - 25/2/2018 |  | 1.5 | Planning
| 2.2 Start setup docker host and tuning kernal | x |  |  | OnSite Visit | 24 - 25/2/2018 |  | 3 | Planning
| 2.3 Setup docker system and tunning | x |  |  | OnSite Visit | 24 - 25/2/2018 |  | 3 | Planning
| 2.4 Deploy mantis system and configure email system (Prototype for WalkThrough) | x | x |  | Remote/Call/Email | 26 - 28/2/2018 |  | 10 | Planning
| 2.5 System WalkThrough/POC/Feature Evaluation |  | x |  | Remote/Call/Email | 1 - 10/3/2018 |  | 20 | Planning
3 | Mantis POC Phase
| 3.1 Discussion, Adjust and finallize configuration for mantis (Redeploy new image) | x | x |  | Remote/Call/Email | 12 - 15/3/2018 |  | 6 | Planning
| 3.2 Training for administrator and end-user | x | x | x | OnSite Visit | 2018-03-17 |  | 8 | Planning
| 3.3 Deploy mantis on production environment | x | x | x | OnSite Visit | 2018-03-18 |  | 8 | Planning
3.4 Implement automation backup
| - Setup shell script for backup database/configuration | x |  | x | Remote/Call/Email | 26-27/3/2018 |  | 4 | Planning
| - Setup autodaily backup and transfer to backup server (FTP, SCP) | x |  | x | Remote/Call/Email | 26-27/3/2018 |  | 4 | Planning
| 3.5 Standby support 1 month | x |  |  | Remote/Call/Email | 1-30/4/2018 |  | N/A | Planning
Remote/Call/Email