## Action_Plan
No | Plan Description | Response Person |  |  | Visit Method | Plan Date/Time | Actual Date/Time | Man Hours | Status | Remark
|  | Implementor | Heng: Dev | Heng: Ops
1 | Preparation Phase
| 1.1 Final Invoice and Payment Document | x | x | x | Remote/Call/Email | 2018-02-19 | 2018-02-18 | 2 | Done
1.2 Start formal inform and request resource
| - Hardware resource for provision docker host | x |  | x | Remote/Call/Email | 19 - 23/2/2018 |  | 1 | Planning
| - VPN access/Remote support solution | x |  | x | Remote/Call/Email | 19 - 23/2/2018 |  | 1 | Planning
| - FTP Server (Backup Server), NTP Server, SysLog etc | x |  | x | Remote/Call/Email | 19 - 23/2/2018 |  | 1 | Planning
| - Collect requirement and design mantis workflow | x | x |  | Remote/Call/Email | 19 - 23/2/2018 |  | 1 | Planning
| 1.3 Confirm Date/Time for site visit (First Times) | x | x | x | Remote/Call/Email | 19 - 23/2/2018 |  | 0.5 | Planning
2 | Onsite Visit & Initial Setup Machine
| 2.1 Join with Heng Dev&Ops team for clarify task |  |  |  | OnSite Visit | 24 - 25/2/2018 |  | 1.5 | Planning
| 2.2 Start setup docker host and tuning kernal | x |  |  | OnSite Visit | 24 - 25/2/2018 |  | 3 | Planning
| 2.3 Setup docker system and tunning | x |  |  | OnSite Visit | 24 - 25/2/2018 |  | 3 | Planning
| 2.4 Deploy mantis system and configure email system (Prototype for WalkThrough) | x | x |  | Remote/Call/Email | 26 - 28/2/2018 |  | 10 | Planning
| 2.5 System WalkThrough/POC/Feature Evaluation |  | x |  | Remote/Call/Email | 1 - 10/3/2018 |  | 20 | Planning
3 | Mantis POC / Golive Phase
| 3.1 Discussion, Adjust and finallize configuration for mantis (Redeploy new image) | x | x |  | Remote/Call/Email | 12 - 15/3/2018 |  | 6 | Planning
| 3.2 Training for administrator and end-user | x | x | x | OnSite Visit | 2018-03-17 |  | 8 | Planning
| 3.3 Deploy mantis on production environment | x | x | x | OnSite Visit | 2018-03-18 |  | 8 | Planning
3.4 Implement automation backup
| - Setup shell script for backup database/configuration | x |  | x | Remote/Call/Email | 26-27/3/2018 |  | 4 | Planning
| - Setup autodaily backup and transfer to backup server (FTP, SCP) | x |  | x | Remote/Call/Email | 26-27/3/2018 |  | 4 | Planning
| 3.5 Standby support 1 month | x |  |  | Remote/Call/Email | 1-30/4/2018 |  | N/A | Planning
Remote/Call/Email

## Docker_Host_Design
No | Description | Value | Remark
1 | Common standard for Host |  | *All host need to access internet by default (Push/Pull Image for Operate)
| - Host Name | dockerserve-<env>-<node number> | <env> = environment name (dev, prd) <node number> = no of node on that environment (4 digits) Start with 0001
| - OS distribution and Version | Ubuntu (16.04 (LTS))
| - CPU allocate per host | 6 vCPU (Mininum) | Upon total container housing consideration
| - Network per Host (NIC) | 1 | 10 Gbps internal connection with Driver VMNET3
| - Standard disk usage for host | 88 GB | - Base for support os and container only. If we have any database placement. It need to consider more on that disk slice - SSD disk type was preferred
| - Memory | 8 GB
| - Partition slice design | / ==> <dockerserve--vg-v-root:15 GB> /home ==> <dockerserve--vg-v-home:10 GB> /var ==> <dockerserve--vg-v-var:35 GB> /tmp ==> <dockerserve-vg-v-tmp: 10 GB> /var/log ==> <dockerserve-vg-v-var_log:10 GB> /swap. ==> <dockerserve--vg-v-swarp: 8 GB> /source<dev> ==> <vgpool-source: 20 GB <optional> /mysql_data_lv==> <vgpool-mysqllv: 30 GB><optional> | All disk slice was consider to use "device-mapper" for easy to manage disk (Reference: https://www.howtogeek.com/howto/40702/how-to-manage-and-use-lvm-logical-volume-management-in-ubuntu/)
| - Server hardening standard | Reference from CIS document | http://www.itsecure.hu/library/image/CIS_Ubuntu_Linux_16.04_LTS_Benchmark_v1.0.0.pdf
| - Linux tunning | <On Discussion>
| - User and role | - User for manage docker configuration: docker | Default Password: Hen9Le@$n9
2 | Docker server housing
| - dockerserve_dev_0001 (Development Environment) | - Mantis_WorkFlow_System
| - IP Address Information | - IP Address: X.X.X.X - Subnet Mask: 255.255.255.0 - Default Gateway: X.X.X.X - DNS Server (Primary / Secondary)
| - NTP Server | - NTP Address 1: X.X.X.X - NTP Address 2: X.X.X.X - NTP Address 3: X.X.X.X
| - SysLog Server | - IP Address: X.X.X.X - Port Connection (UDP/TCP): - Port Number (XX):
| - Monitoring Agent Install/Configruation Type | - SNMP IP Address: X.X.X.X - Community String: XXXX - Nagios Client to Install ? - Standard Configuration for Nagios.cfg ?
| - Backup Information | - Path to backup (/mysql_data, etc) - Backup Method (Veem backup linux, FTP outside etc) | Upon design of data to blind mount
| - dockerserve_prd_0001 (Production Environment) | - Mantis_WorkFlow_System | Disk slice for registry is upon final sizing for image store
| - IP Address Information | - IP Address: X.X.X.X - Subnet Mask: 255.255.255.0 - Default Gateway: X.X.X.X - DNS Server (Primary / Secondary)
| - NTP Server | - NTP Address 1: X.X.X.X - NTP Address 2: X.X.X.X - NTP Address 3: X.X.X.X
| - SysLog Server | - IP Address: X.X.X.X - Port Connection (UDP/TCP): - Port Number (XX):
| - Monitoring Agent Install/Configruation Type | - SNMP IP Address: X.X.X.X - Community String: XXXX - Nagios Client to Install ? - Standard Configuration for Nagios.cfg ?
| - Backup Information | - Path to backup (/mysql_data, etc) - Backup Method (Veem backup linux, FTP outside etc) | Upon design of data to blind mount
3 | Docker installation
| - version control | - 17.12 CE Edition
| - Storage driver | - Overlay2

## Docker_Container_Design
No | Description | Value | Remark
System Name: MantisWF (Mantis WorkFlow)
| - Image name/Tags: | MantisWF_<comp>_<version control> | <comp> = component of system (web, db, webdb, app, batch etc) <version control> = BASE/RC/FINAL_X.X.XX < RC = Release Control (Develop Manager Commit Only) FINAL = Final Release (For promote to production environment) (X)First Digit = Major version of software (0-9), (X)Second Digit = Sub version of software (0-9), (XX)Third Digit = Development sub version (on development)(0-99)>
| - Base Image: | php:7.2apache (web), mysql (db),phpmyadmin (webdb) | Store image for reference: MantisWF_web_BASE_1.0.00 MantisWF_db_BASE_1.0.00 MantisWF_webdb_BASE_1.0.00
| - Network Configuration | dev_general_network | docker network create --driver bridge \ --subnet=192.168.201.0/24 --ip-range=192.168.201.0/24 \ --gateway=192.168.201.5 --opt="com.docker.network.mtu"="1500" dev_general_network
| - Network Configuration | prd_general_network | docker network create --driver bridge \ --subnet=192.168.202.0/24 --ip-range=192.168.202.0/24 \ --gateway=192.168.202.5 --opt="com.docker.network.mtu"="1500" prd_general_network
Development Environment
Web Container
| -URL: | http://mantiswf.com, http://x.x.x.x::8011 <Direct>
| -Container Name: | web_mantiswf
| -Network | --net dev_general_network
| -Map Port (-p) | -p 8010:80 | Map port host 8010 to 80 of container
| -Volume Map (-v) | --mount type=bind,source=/home/docker/source/web_mantiswf,target=/app \ --mount type=bind,source=/home/docker/dockers/web_mantiswf/logs,target=/opt/bitnami/nginx/logs \ --mount type=bind,source=/home/docker/dockers/web_mantiswf/nginx,target=/bitnami/nginx \ | For development we will map source code of system on docker host for easy to change coding
| - Docker run command | docker container run -dt --name web_mantiswf -p 8010:8080 \ --mount type=bind,source=/home/docker/source/web_mantiswf,target=/app \ --mount type=bind,source=/home/docker/dockers/web_mantiswf/logs,target=/opt/bitnami/nginx/logs \ --mount type=bind,source=/home/docker/dockers/web_mantiswf/nginx,target=/bitnami/nginx \ --net dev_general_network --net-alias php_mantiswf \ bitnami/nginx:latest | Final when all test done
PHP Container
| -Container Name: | php_mantiswf
| -Network | --net dev_general_network
| -Map Port (-p) | N/A | No need due to denied access database directly
| -Volume Map (-v) | --mount type=bind,source=/home/docker/source/web_mantiswf,target=/app \ --mount type=bind,source=/home/docker/dockers/web_mantiswf/phpfpm,target=/bitnami/php-fpm \ | Map data of mysql to ourside
| - Docker run command | docker container run -dt --name php_mantiswf \ --mount type=bind,source=/home/docker/source/web_mantiswf,target=/app \ --mount type=bind,source=/home/docker/dockers/web_mantiswf/phpfpm,target=/bitnami/php-fpm \ --net dev_general_network --net-alias php_mantiswf \ bitnami/php-fpm:7.2 | Final when all test done
DB Container
| -Container Name: | mysql_mantiswf
| -Network | --net dev_general_network
| -Map Port (-p) | N/A | No need due to denied access database directly
| -Volume Map (-v) | --mount type=blind,/mysql_data/mantiswf,target=/var/lib/mysql | Map data of mysql to ourside
| - Docker run command | docker container run -dt --name mysql_mantiswf \ --mount type=bind,source=/mysql_data_lv/mysql_mantiswf,target=/bitnami \ --net dev_general_network --net-alias mysql_mantiswf \ -e MARIADB_ROOT_PASSWORD=Heng_99 -e MARIADB_DATABASE=mantiswf \ bitnami/mariadb:latest | Final when all test done
Phpmyadmin Container
| -URL: | http://phpmyadmin.com. , http://x.x.x.x:8011 <Direct>
| -Container Name: | phpmyadmin_mantiswf
| -Network | --net dev_general_network
| -Map Port (-p) | -p 8011:80
| -Volume Map (-v) | --mount type=bind,source=/mysql_data_lv/phpmyadmin_mantiswf,target=/bitnami
| - Docker run command | docker container run -dt --name phpmyadmin_mantiswf -p 8011:80 \ --mount type=bind,source=/mysql_data_lv/phpmyadmin_mantiswf,target=/bitnami \ -e PHPMYADMIN_ALLOW_ARBITRARY_SERVER=true \ --net dev_general_network --net-alias phpmyadmin_mantiswf \ bitnami/phpmyadmin:latest | Final when all test done
Load Balance Container
| -URL: | x.x.x.x:80, x.x.x.x:443
| -Container Name: | lb
| -Network | --net dev_general_network
| -Map Port (-p) | - 80:8080, -p 443:8443
| -Volume Map (-v) | --mount type=bind,source=/home/docker/dockers/lb/logs,target=/opt/bitnami/nginx/logs \ --mount type=bind,source=/home/docker/dockers/lb/nginx,target=/bitnami/nginx \
| - Docker run command | docker container run -dt --name lb -p 80:8080 -p 443:8443 \ --mount type=bind,source=/home/docker/dockers/lb/logs,target=/opt/bitnami/nginx/logs \ --mount type=bind,source=/home/docker/dockers/lb/nginx,target=/bitnami/nginx \ --net dev_general_network --net-alias lb \ bitnami/nginx:latest | Final when all test done